## Project Timeline
Motor Control Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Description | Milestone | Position | Baseline | Project Timeline Tip
2022-03-29 | Project Start |  | 20 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2022-04-07 | Milestone 1 | Define project timeline | 10 | 0
2022-04-12 | Milestone 2 | Milestone 2 | -10 | 0
2022-04-19 | Milestone 3 | Milestone 3 | 25 | 0
2022-04-26 | Milestone 4 | Milestone 4 | -15 | 0
2022-05-03 | Final Exam | Project demonstration | 15 | 0

## week 1
Weekly Milestone Description | Milestone Number
Define project timeline and layout. Establish communication with terminal and Matlab client. | 1
What have you accomplished this week?
I answered all project layout questions, sketched a wiring diagram of the connections between the NU32 and the peripherals. I populated a block diagram which helped me understand the interactions of the various parts of this project. I established communication between the PIC32 and the terminal and Matlab client. I implemented an adding menu function and verified performance between Matlab and the microcontroller.
What problems have you encountered?
I was unsure of how to answer many of the project layout questions.
What have you done to overcome these problems?
I refered back to chapters that covered the things I was confused about. I also reviewed old cold to help me recall how to interface over UART. This helped me get back up to speed and answer the project layout questions.
What do you plan to do next week?
Next week I plan to focus on implementing encoder functions and wiring the current sensor.

## week 2
Weekly Milestone Description | Milestone Number
Implement encoder functions. Current sensor wiring and calibration. | 2
What have you accomplished this week?
Implemented encoder wiring and ability to read encoder counts in both counts and degrees. Tested encoder performance, and organized wiring. Wired the current sensor and selected resistors for the circuit.
What problems have you encountered?
The encoder would require two reads to get an updated value. Determining how to go from counts to degrees.
What have you done to overcome these problems?
I found that multiple reads of the encoder were necessary and updated the code as such. Consulting the datasheet helped me determine the encoder counts per revolution, allowing me to convert from counts to degrees.
What do you plan to do next week?
Test current sensor by reading from ADC. Implement low-level motor current control by wiring H-bridge and implementing code.

## week 3
Weekly Milestone Description | Milestone Number
Read from the current sensor using ADC. Low-level motor current control using PWM and an H-bridge. This will enable control of the motor using a PWM signal from the client. | 3
What have you accomplished this week?
What problems have you encountered?
What have you done to overcome these problems?
What do you plan to do next week?

## week 4
Weekly Milestone Description | Milestone Number
Tune PI current control for ITEST performance. Implement and tune position control and trajectory tracking. | 4
What have you accomplished this week?
What problems have you encountered?
What have you done to overcome these problems?
What do you plan to do next week?